## Project charter
Project Charter
Project- SpectroGuard
PROJECT PARTICIPANTS
Name | SPECTROGUARD
Stakeholder | Project Sponsors | Marathwada Mitra Mandal's Institute of Technology
| Customers | Technical and Non-Technical global users
Project Manager | Project Manager | Kapil Waghumbare
| Assistant Project Manager | Pratiksha Alhat
Email | kapilwaghumbare@gmail.com
Project Team | Kapil Waghumbare, Pratiksha Alhat, Shraddha Gadekar.
PROJECT DESCRIPTION
Goal Statement | To design and develop a user-friendly web-based cybersecurity toolkit containing four security models. A password predictability checker trained using a higher-order Markov model, a URL safety validator using blacklist and heuristic analysis, an AI-based phishing website detector using a support vector machine, and a document validator using SHA-256.
Objective | To develop an intuitive web platform that mitigates social engineering risks for non-technical users by providing automated, real-time verification of malicious links and counterfeit login pages.

## Gantt chart
Project- SpectroGuard
Sr. No. | Tasks | Phase 1 | [6 empty] | Phase 2 | [6 empty] | Phase 3 | [6 empty] | Phase 4 | [6 empty] | Phase 5 | [6 empty] | Phase 6
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37
|  | 2025-09-23 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29
1 | Data Collection
Gather Data sets | bar: 2025-09-23 to 2025-10-24
2 | Data Preprocessing
Data Cleaning | bar: 2025-10-24 to 2025-11-14
Data Optimization | bar: 2025-10-24 to 2025-11-14
3 | Model Development 1
Password Model development | bar: 2025-11-07 to 2025-12-12
Training | bar: 2025-11-07 to 2025-12-12
Testing | bar: 2025-11-21; 2025-12-05 to 2025-12-12
4 | Model development 2
URL Model development | bar: 2025-12-12 to 2026-01-09
Training | bar: 2025-12-12 to 2026-01-09
Testing | bar: 2025-12-26; 2026-01-09 to 2026-01-16
5 | Model Development 3
Phishing Model development | bar: 2026-01-16 to 2026-02-20
Training | bar: 2026-01-16 to 2026-02-20
Testing | bar: 2026-01-30; 2026-02-13 to 2026-02-27
6 | Model Development 4
Hash Model development | bar: 2025-11-07 to 2025-11-14
7 | Comparison Analysis
Algorithm development & Testing | bar: 2026-02-27 to 2026-04-17
Comparison matrix development | bar: 2026-04-17
8 | User Interface
development of UI/UX | bar: 2026-02-27 to 2026-04-24
9 | Integration | bar: 2026-04-24 to 2026-05-15
10 | Deployment | bar: 2026-05-15 to 2026-05-29
11 | Documentation
[6 empty] | 2025-10-23 | 2025-10-20 | 2025-11-10 |  | 2025-11-15 | Weekly |  | 2025-12-15 | 2025-12-13 |  | Weekly |  | 2026-01-20 | 2026-01-18 |  | Weekly |  |  | 2026-03-01 | 2026-02-26 | [6 empty] | 2026-04-26 | 2026-04-25 |  | 2026-05-16 | 2026-05-15

## RACI
RACI Matrix
Project -SpectroGuard
Sr. No. | Task | Kapil | Pratiksha | Shraddha | Swapnil Sir | Responsible
0.1 | Project charter | R | C | C | A | Accountable
0.2 | WBS and Gantt chart | A/R | R | C | I | Consulted
0.3 | Risk log | A/R | R | C | I | Informed
0.4 | Progress tracking and guide reviews | A/R | R | C | C
1.1 | Gather datasets | A/R | I | R | I
2.1 | Data cleaning | A | I | R | I
2.2 | Data optimization | A/R | I | C | I
3.1 | Password model development | A/R | C | I | I
3.2 | Password model training | A | R | I | I
3.3 | Password model testing | A | R | I | I
4.1 | URL model development | A/R | C | I | I
4.2 | URL model training | A | R | I | I
4.3 | URL model testing | A | R | I | I
5.1 | Phishing model development | A/R | C | I | I
5.2 | Phishing model training | A | R | I | I
5.3 | Phishing model testing | A | R | I | I
6.1 | Hash model development | A | C | R | I
7.1 | Algorithm development | A/R | C | C | C
7.2 | Comparison matrix | A/R | C | C | C
8.1 | UI/UX development | A/R | C | C | I
9 | Integration | A | C | R | I
10 | Deployment | A | C | R | I
11 | Final demo and approval | R | R | R | A

## WBS
Work Breakdown Strecture
Project- SpectroGuard
Sr. No. |  | Work Breakdown | Task Owner | Start Date | Due date | Buffer days | Final Due Date | Task completed
1 | Data collection
| 1.1 | Gather Data sets | Kapil Waghumbare | 2025-09-23 | 2025-10-17 | 3 | 2025-10-20 | 100
Shraddha Gadekar
2 | Data Preprocessing
| 2.1 | Data Cleaning | Shraddha Gadekar | 2025-10-23 | 2025-11-01 | 7 | 2025-11-15 | 100
| 2.2 | Data Optimization | Kapil Waghumbare
3 | Model development 1
| 3.1 | Password Model development | Kapil Waghumbare | 2025-11-10 | 2025-12-01 | 9 | 2025-12-10 | 100
| 3.2 | Training | Pratiksha Alhat
| 3.3 | Testing | Pratiksha Alhat | 2025-12-11 | 2025-12-12 | 1 | 2025-12-13 | 100
4 | Model development 2
| 4.1 | URL Model development | Kapil Waghumbare | 2025-12-15 | 2026-01-05 | 10 | 2026-01-15 | 100
| 4.2 | Training | Pratiksha Alhat
| 4.3 | Testing | Pratiksha Alhat | 2026-01-16 | 2026-01-17 | 1 | 2026-01-18 | 100
5 | Model development 3
| 5.1 | Phishing Model development | Kapil Waghumbare | 2026-01-20 | 2026-02-10 | 10 | 2026-02-20 | 100
| 5.2 | Training | Pratiksha Alhat
| 5.3 | Testing | Pratiksha Alhat | 2026-02-22 | 2026-02-23 | 3 | 2026-02-26 | 100
6 | Model development 4
| 6.1 | Hash Model development | Shraddha Gadekar | 2025-11-10 | 2025-11-13 | 2 | 2025-11-15 | 100
7 | Comparison Analysis
| 7.1 | Algorithm development | Kapil Waghumbare | 2026-03-01 | 2026-04-01 | 10 | 2026-04-11 | 100
| 7.2 | Comparison matrix development | Kapil Waghumbare | 2026-04-12 | 2026-04-20 | 3 | 2026-04-23 | 100
8 | User Interface
| 8.1 | development of UI/UX | Kapil Waghumbare | 2026-02-27 | 2026-04-19 | 6 | 2026-04-25 | 100
9 | Integration |  | Shraddha Gadekar | 2026-04-26 | 2026-05-05 | 10 | 2026-05-15 | 100
10 | Deployment |  | Shraddha Gadekar | 2026-05-16 | 2026-05-22 | 6 | 2026-05-28 | 100
Formulas:
Final Due Date = [Due date]+[Buffer days]

## Risk Log
Rick Log
Project- SpectroGuard
Risk ID | Risk | WBS Ref | Probability | Impact | Score | Mitigation | What Happened | Action Taken | Occurred? | Date | Final Status
R1 | Password model not learning patterns while training | 3.1, 3.2, 3.3 | 3 | 4 | 12 | Check and optimize data set before training | Password model was not able to learn patterns, which caused predictability issue | Changed data set and optimized it according to the higher order | Yes | 2025-11-29 | Closed
R2 | URL model accuracy under target | 4.1, 4.2, 4.3 | 3 | 5 | 15 | Check data set and train-test split before training | Accuracy was not up to the target (93%+) | Retrained the URL model with more data | Yes | 2026-01-07 | Closed
R3 | Phishing model file corrupted | 5.1, 5.2, 5.3 | 2 | 4 | 8 | Keep backups and version control for trained models | Phishing model was not able to fetch features from a website | Restored model from Google Drive. Backup was an older version, so modified it to work with current Python version (3.14.3) | Yes | 2026-02-23 | Closed
R4 | Python version may not match the backend | 8, 9 | 2 | 2 | 4 | Check version requirements for development and keep track of them | Not applicable | Not applicable | No | Not applicable | Not occurred